## Term Project CS 633 teams
Team Member | Role | 2018-01-23 | 2018-01-30 | 2018-02-06 | 2018-02-13 | 2018-02-20 | 2018-02-27
Patty Thrall | Project Manager | 2018-01-23: Propose Project Scope; 2018-02-06: Estimation Record; 2018-02-27: Submit draft report with all deliverables Final team's presentation of App (All team members)
Mike Smith | Developer | Propose Team Composition | Begin Coding |  | Converge on Component Interaction Diagram | Complete Coding
Gabriel Rua | Requirements | Create Pivotal Tracker (All Team members Join) Distribute Initial Report for weekly Deliverables | Document five Personas(RASCI) Converge on five Requirements in cononical form in Pivotal Tracker |  | Document State Transitions | Transform Mock-ups into Wireframes
Giuseppe Vaccaro | Tester | Register With GIT and create repo (All Team Members) | Document Tools Connectivity Digram | Provide List of Configuration Items | Document four use cases using UML |  | Document two Test cases in standard form Reduce data-driven Combinations using all Pairs
Yigit Katkici | TBD