## Slide 1: Term project report Met CS 633 OL s 2018
Team Members:
Giuseppe Vaccaro Michael Smith Yigit Katkici
Patty Thrall Gabriel Rua
Group: Zac(3)
Notes: Smart Phone image created with https://placeit.net/stages/frontal-mockup-of-a-white-iphone-6-plus-over-a-transparent-background-a11471
FitForMe Logo created with https://www.tailorbrands.com/

## Slide 2: Agenda
Project Scope
Product Design
Application Overview
Defect Management
Product Demonstration
Retrospective
Q&A
Patty

## Slide 3: Project Scope

## Slide 4: Project Overview
Project: | Fit For Me, a Fitness and Health Website and App |  |  |  |  |  | 
Objective | To create a web-based application for users to create an account and enter body measurements and current reps in the gym, then users can go in and create new entries showing their improvements from their previous entries. |  |  |  |  |  | 
High Level Customer Features | Design workout routines Establish and track progress toward goals |  |  |  | Measure performance Integrated exercise reference guide | In-app meal planner Find training partners and personal trainers | 
Project Team |  |  |  | Milestones |  |  | 
Katkici, Y. |  | Developer |  | Concept & Scope Defined |  |  | Jan 23
Rua, G. |  | Requirements |  | Personas & Requirements Defined |  |  | Jan 30
Smith, M. |  | Developer |  | Estimation Review & CI List |  |  | Feb 6
Thrall, P. |  | PM |  | Use Cases & Interactions Defined |  |  | Feb 13
Vaccaro, G. |  | Tester |  | Mock-ups & Wireframes |  |  | Feb 20
 |  |  |  | Testing & Launch |  |  | Feb 27
Patty

## Slide 5: User Personas
 | Customer User | Trainer User | Administrator | Automation User | Meal Prep Tracker
Goals | Erica wants to find a place to log her accomplishments when she goes to the gym hoping to find motivation to get into the gym at a more consistent basis | Caroline wants to be able to create workout sessions and help people with their fitness goals | Mike wants to onboard as many customers as possible by introducing workouts and trainers to customer users on a user-friendly site | The automaton performs routine tasks such as resetting user passwords and managing the interface between the application and 3rd party components | The meal prep tracker is responsible for monitoring nutritional intake, proposing diet plans and providing other guidance to customers in light of their goals
Background | 25 year old, employed full time. Has a significant other with one dog Loves to play tennis Occasionally goes to the gym. It is difficult to find the time | Has been a personal trainer for over 20 years Expertise in Yoga (all levels), endurance training, dance, gymnastics, weightlifting, spinning Currently training in Washington | Mike is a computer programmer Mike created this website application | Create customer user account and trainer user account Ability to help customer users | Ability to calculate numbers Provide numbers for customer users
Scenarios | Erica is not technical and wants a user friendly website Erica would like to have easy access to the website as she would otherwise not log in | Caroline needs a website to be able to feedback to her clients about their fitness journeys Caroline would like to have an easier way to communicate | Continue to update the website Receive feedback to improve the user experience | Create account when customer joins Provide new password when customer requests one Delete account upon customer requests | Provide how many calories the customer user should be eating per weight goals Provide how many calories are left for the day for the customer user
Patty

## Slide 6: RASCI Stakeholders
Patty
Task/Deliverable | Customer User | Trainer User | Administrator | Automation User | Meal Prep Tracker
Register for an account | C | C | A | I | -
Update user profile & measurements | R | - | I | I | -
Add workouts | A | A | R | I | -
Log food intake | A | S | R | - | R
Update improved measurements | R | - | I | I | -

## Slide 7: Configuration Items List
Item No. | Configuration Item Name | Version | Submission Date | Owner | Repository
1 | Scope Document | 1.0 | 2018-01-22 | Patty Thrall | GitHub
2 | Definition of Users | 1.0 | 2018-01-22 | Patty Thrall | GitHub
3 | Engineering Requirements List | 2.0 | 2018-02-11 | Gabriel Rua | PivotalTracker
4 | Estimation Record | 1.0 | 2018-02-06 | P. Thrall & G. Rua | GitHub
5 | Definition of Use Cases | 1.0 | 2018-02-12 | P. Thrall & G. Rua | GitHub
6 | Front-end Application Development | 1.0 | 2018-02-24 | Michael Smith | GitHub
7 | Back-end Application Development | 1.0 | 2018-02-24 | Yigit Katkici | GitHub
8 | Test Cases | 1.0 | 2018-02-24 | Giuseppe Vaccaro | GitHub
9 | Defect Tracking – Test Cases | 1.0 | 2018-02-24 | Giuseppe Vaccaro | GitHub
10 | Defect Tracking – Peer Review | 1.0 | 2018-02-25 | Team | GitHub
11 | Configuration Item List | 2.0 | 2018-02-12 | Giuseppe Vaccaro | GitHub
12 | Interaction Diagram | 2.0 | 2018-02-12 | Yigit Katkici | GitHub
13 | State Transitions | 2.0 | 2018-02-11 | Giuseppe Vaccaro | GithHub
Giuseppe

## Slide 8: Estimation Record
Patty
 |  | Size Measure | Typical Effort per Size Measure (person hours) | Size | Effort Person/Hours |  | Final (Fibonacci) | Actual
 |  |  |  |  | Expert A | Expert B |  | 
Requirements | Definitions of users (personas) | # roles | 0.2 | 5 | 1 | 1 | 1 | 3
 | Definition of scope and limitations | # attributes | 0.1 | 10 | 1 | 1 | 1 | 2
 | Engineering Requirements List | # requirements | 0.4 | 30 | 12 | 15 | 21 | 40
Configuration Management | Configuration Items List | # CI items | 0.09 | 13 | 1 | 0.5 | 1 | 2
Estimation | Estimation Record | # activities | 0.08 | 13 | 1 | 1 | 1 | 1
Design | State Transition Diagram | # states | 0.25 | 4 | 2 | 1 | 2 | 1
 | Definition of use cases | # use cases | 0.5 | 4 | 2 | 2 | 2 | 3
 | Definition of Fields | # fields | 0.1 | 20 | 2 | 2 | 2 | 2
 | Definition of Reports | # reports | 1 | 2 | 2 | 2 | 2 | 2
Peer Reviews | Issues from peer reviews attained | # issues | 0.16 | 25 | 3 | 5 | 5 | 5
Implementation | FitFOrMe | # User screens | 6 | 1 | 6 | 8 | 8 | 21
Test Design | Test Cases | # test cases | 0.33 | 6 | 2 | 1 | 2 | 6
Test Execution | Defects from Testing recorded | # defects | 0.3 | 10 | 3 | 3 | 3 | 21

## Slide 9: Estimation Accuracy
Patty

## Slide 10: Product Design

## Slide 11: Backlog
Register & Log-in
Measurements & Goals
Design Workout
Track Workout
Food Diary
Website Administration
Tracker Integration
Import/Export Function
User Epics
Technical Epics
Gabriel
Pivotal Tracker

## Slide 12: User Stories
ID | Backlog Item
Customer User - Erica | 
154705102 | As a Customer User, I want to be able to enter workout schedule by day and muscle group so that I can share it with potential partners and trainers.
154705103 | As a Customer User, I want to be able to select from a pre-existing list of available exercises so that I can readily build a workout routine
154705109 | As a Customer User, I want to be able to combine selected exercises into routines so that I can plan a workout that corresponds to my health goals
154705111 | As a Customer User, I want the application to track the number of reps that I can do of a certain weight by type of exercise and muscle group so that I can gauge whether I am becoming stronger
154705114 | As a Customer User, I want the application to track my performance during strength sets so that I know whether I am becoming better at anaerobic exercises
154705116 | As a Customer User, I want the application to measure performance during cardio sets so that I know whether I am becoming better at aerobic exercises
154705117 | As a Customer User, I want to be able to enter a goal that I want to reach within a specific time window of weeks or months so that I can keep track of my progress toward that goal
154705125 | As a Customer User, I want a link to videos or graphics showing correct form for an exercise so that I can learn and ensure safe and correct execution of the exercise
154705127 | As a Customer User, I want to be able to import from external data source, e.g. Excel, so that I can combine data not stored in the application with data that exists there
154705128 | As a Customer User I want to be able to export data to multiple formats, e.g. Excel, csv, XML in order to be able to perform ad hoc analysis and reports not available in the application.
ID | Backlog Item
Customer User - Erica | 
154705131 | As a Customer User, I want to select from a known list of predefined workout routines so that I do not have to come up with one myself.
154705135 | As a Customer User, i want to be able to periodically enter body measurements so that I can evaluate whether I am progressing towards my goals.
154705137 | As a Customer User, I want to see a graphical display of body measurements history so that I have a clear visual indicator of my progress over a specific time period.
154705138 | As a Customer User, I want to see a graphical display of my performance so that I have an easy method for identifying a trend.
154705142 | As a Customer User, I want to be able to match the duration of my workout to a playlist of music so that I do not have to look at my watch during the routine.
154705146 | As a Customer User, I want to be able to keep a food intake diary so that I can understand whether my food choices support my nutritional goals
154705150 | As a Customer User, I want to be able to load pictures for a specific date or workout so that I have a visual record of my progress towards a goal.
154705153 | As a Customer User, I want to be able to note strengths and weakness during a workout so that I can learn where I'm doing well and where I need to improve
154705154 | As a Customer User, I want to be able to add notes to a specific workout so that I can track such variables as mood, location, and training partner and how they affect my workout routine.
154723101 | As a Customer User, I want to be able to provide feedback on the application so that design, support and administration teams receive my suggestions for improvements.
Gabriel

## Slide 13: User Stories
ID | Backlog Item
Application Service – Automation User | 
155113518 | As the Automation user, I need to validate log-in credentials so that users can access the system securely
154705118 | As the Automation User, I need to be able to track performance against a user's goal(s) so that I can alert him to progress at defined milestones, for example 25% of goal reached.
154705121 | As the Automation User, I want to present the user an estimate of calories burned so that the user knows whether s/he is reaching the goals for a particular session
154705126 | As the Automation User, I need to interface to external devices such a smart phone or fit bit so that I can recognize and record when the user is performing certain exercises without the user having to input the data.
154705132 | As the Automation User, I need the user to select a gender so that I can correctly perform calculations related to necessary food intake and body mass.
154705133 | As the Automation User, I need the user to enter age so that I can correctly perform calculations related to necessary food intake and body mass.
154705152 | As the Automation User, I need to interface to a food database with calories of common food and portions so that the user can make decisions regarding food choices that appropriately support the user's weight-loss or weight-gain goals.
154706538 | As the Automation User, I need to be able to generate and send a new password so that the user can regain access to the application in case of forgotten passsword
154706540 | As the Automation User, I need to be able to send the user an email confirming registration so that the user knows the registration succeeded.
155077695 | As the Automation user, I need to support SSO so that users can log-in to the application with their existing Facebook or Google accounts.
155113497 | As the Automation user, I need to capture a username, password and e-mail address so that users can register with the system.
ID | Backlog Item
Trainer User - Caroline | 
154722814 | As a Trainer User, I want to be able to find other people using the app so that I can offer them my professional services
154722845 | As a Trainer User, I want to be able to see my customers' performance history and goals so that I can recommend specific workout and dietary actions that support their goals
Administrator - Mike | 
154706518 | As the Administrator, I want to be able to see the full list of users so that I can ensure system resources match projected user base needs
154706521 | As the Administrator, I want to be able to delete an account so that the current list of users corresponds to desired and active accounts
154706524 | As the Administrator, I want to be able to update a user account so that I can keep the records current
Application Service - Meal Prep Tracker | 
154722899 | As the Meal Prep Tracker User, I need to be able to calculate the nutritional values of a meal so that the user knows how many calories, carbs, etc. that s/he has ingested.
154722942 | As the Meal Prep Tracker User, I need to be able to suggest to the user a daily or weekly meal plan that supports the goals the user has entered into the application
154722975 | As the Meal Prep Tracker User, I need to be able to keep track of the user's daily meal intakes so that I can inform the user of remaining nutritional requirements for the day.
Gabriel

## Slide 14: Register & Login Use Case
Patty
Notes: UML diagram created with MagicDraw

## Slide 15: Enter Measurements Use Case
Patty
Notes: UML diagram created with MagicDraw

## Slide 16: Design a Workout Use Case
Patty
Notes: UML diagram created with MagicDraw

## Slide 17: Record Food Intake Use Case
Patty
Notes: UML diagram created with MagicDraw

## Slide 18: Register & Login State Transition
Giuseppe

## Slide 19: Workout Tracker State Transition
Giuseppe

## Slide 20: Components Diagram
Yigit

## Slide 21: Wireframes

## Slide 22: Register & Login
Homepage
Register
Login
Gabriel
Notes: Mock-ups created with BalsamIQ

## Slide 23: Capture Measurements
My Plan
Edit Profile
Capture Stats
Gabriel
Notes: Mock-ups created with BalsamIQ

## Slide 24: Design Workout & Track Food
Design Workout
Enter Goal
Record Food Intake
Gabriel
Notes: Mock-ups created with BalsamIQ

## Slide 25: Application Overview

## Slide 26: Application Overview
Django Application
Python Language
Hosted on Heroku
Postgres database
Mike

## Slide 27: Tools & Technology
Mike

## Slide 28: Defect Management

## Slide 29: Peer Reviews
Product | Date | Producer | Reviewer | Comment | Outcome
Scope Document | 2018-01-22 | Patty | Gabriel | Pivotal Tracker and GitHub are missing from scope document | Added missing tools
Project Scope | 2018-01-22 | Patty | Giuseppe | Misspelling of Slack | Document revised
Policy Document | 2018-01-23 | Gabriel | Mike | Misspelling of word requirements | Document revised
Project Report | 2018-01-23 | Gabriel | Giuseppe | Misspelling of name | Document revised
Use Case UML | 2018-02-12 | Gabriel | Giuseppe | The use case diagram looks like a state diagram. | Corrected the diagram
Mock-ups | 2018-02-17 | Gabriel | Mike | Wireframes are beyond tools’ capabilities | Mock-ups revised
Code: Views.py | 2018-02-18 | Mike | Yigit | User can attempt an action requiring authentication while not authenticated. | Corrected the code.
Log stats screen | 2018-02-18 | Yigit | Patty | It is not possible to enter a decimal point in BMI field | Not corrected
Test Cases | 2018-02-25 | Giuseppe | Gabriel | The test case has two results – one positive and one negative | Split test cases
Mike

## Slide 30: Test Cases – Create Account (NEG)
Giuseppe

## Slide 31: Test Cases – Log In (POS)
Giuseppe

## Slide 32: Test Cases – Log Meas. & Routine
Giuseppe

## Slide 33: Data Driven Combinations
TEST CASES |  |  |  | 
case | Function | user | source | pairings
1 | Register | trainer | internal | 3
2 | Register | customer | external | 3
3 | Log-in | trainer | external | 3
4 | Log-in | customer | internal | 3
5 | Log meals | trainer | internal | 2
6 | Log meals | customer | external | 2
7 | Log info | trainer | external | 2
8 | Log info | customer | internal | 2
9 | Log workout | trainer | internal | 2
10 | Log workout | customer | external | 2
11 | Log schedule | trainer | external | 2
12 | Log schedule | customer | internal | 2
Giuseppe

## Slide 34: Defects Discovered
Giuseppe

## Slide 35: Product Demonstration

## Slide 36: Demo
https://fitforme.herokuapp.com
Yigit

## Slide 37: Retrospective

## Slide 38: Lessons Learned
— G. Vaccaro
— Y. Katcici
Lorem ipsum dolor sit amet, consectetur adipiscing elit. Praesent finibus turpis at lacinia venenatis. Morbi laoreet tortor dolor, sed luctus tellus lacinia.
When mapping test cases to use cases, a lot of variables have to be considered. Using AllPairs was helpful in narrowing down and organizing test cases.
— M. Smith
The Django Framework is a solid way to build web applications.
The communication was spot on. We were able to chat anytime throughout the week through Slack. Using GitHub was a challenge. In the future, I would like to play more with GitHub.
— P. Thrall
Collaboration was great. We could have used Pivotal Tracker better. Adding prep activities as sub-stories or tasks to stories will help produce better estimates.
— G. Rua

## Slide 39: Feedback
Q&A
ANSWERS
QUESTIONS
Comments
Suggestions

## Slide 40: Appendix

## Slide 41: Weekly Feedback
Review

## Slide 42: Zac Feedback
Week 1
Observations:
Looks like your team is off to a great start! I really like the idea of a health app; it is certainly becoming a fast-growing application space. Your scope/objective page is excellent. Great job on creating comprehensive stories – they really help paint a good picture of what you will be building. Your policy doc also looks great – it shows a lot of thought and care went into the early stages of the project, which is important; contributors need to know what’s expected of them and how to operate as a team. I really like how structured your communication appears. I like all the activity in Slack, and Pivotal. I really enjoy your epics in Pivotal – they really paint the picture of the work well.
Insights:
Very impressed with the organization of the epics. I enjoy how they are organized in a nice, clear “happy path” to deliver the value to the user. I am slightly concerned that I don’t see any mention of Personas. Perhaps this is an oversight? I would certainly add contextual value to your stories. It does seem like you have them in your stories, but perhaps they aren’t clearly defined – for I see a mix of “Meal Prep User” and “registered user” – are they one in the same? A section in your documentation that describes each persona would certainly be helpful in this regard.
All in all, it certainly looks like you are off to a great start. I can’t wait to see how this project turns out!

## Slide 43: Zac Feedback
Week 2
Observations:
Great work this module. It looks like your team is really hitting it’s stride, and producing some great stuff. Your persona deliverable is excellent – I get a great sense of the potential users of the system, and their potential needs and desires. Your summary powerpoint continues to be excellent – very well organized and presented; nice and polished – keep up the amazing work there!
Insights:
I continue to be impressed with the level of organization of this team. The work I see in Pivotal, and the communication I see in slack shows that thought and care is being taken – so continue that trend and you will have great success. I am really impressed with the level of collaboration and communication that this team displays – it will certainly aid you in the end, and your project will reflect the quality of your collaboration. If I had anything to tweak/suggest for improvement, it might be this; I hope by now that some coding has started (judging from your milestones, it appears it has already had some great progress). To that end – it would be nice if you could please provide access to the code repository you are using (github, etc). Since this is not a programming course, we will not be judging the code itself, but more of the process that you are using to develop (branching strategies, code reviews, etc). Github, and other public repositories really help demonstrate those things, so any insight into your repo would be much appreciated.

## Slide 44: Zac Feedback
Week 3
Observations:
Awesome stuff this week! First off, I really like the update to the persona’s page – it’s much cleaner and easier to get the full picture, great job there. For this week’s deliverables – great job on the CI list – it seems very complete and thorough. Your Estimation Record is also great – it really captures the totality of the project. As always – formatting and look/feel is spot-on. Very polished. Great job there – keep it up!
Insights:
Great job on the CI List – I like how you’ve already identified roles/responsibilities for the upcoming deliverables – shows really good organization and foresight. As for the estimation record – everything looks good. I just have one piece of feedback (and don’t worry – it was common amongst all the projects, so you’re not alone). For the Estimation item: “Implementation” – perhaps it’s a bit too high level? Trying to estimate the totality of the development work could be rather difficult to be accurate. Special tip: in next week’s module, you will be asked to provide a Component Interaction Diagram, meaning you will need to break up the development work into components. Perhaps it would be easier to estimate, and more accurate, if you were to provide estimates at the component level – so that the “Implementation” line item is broken down further. Other than that – everything is looking incredible, and I’m continually impressed with your hard work thus far. Keep it up – halfway there!

## Slide 45: Zac Feedback
Week 4
Observations:
Awesome stuff this week, again! I continue to be impressed with the quality of the work being produced by this team! I am very impressed by your Component Interaction Diagram – I really enjoy the format that you used, very clear and concise.
Insights:
I continue to be impressed by the activity I’m seeing from this team on slack. Your PowerPoint is coming along nicely. I really like the name and logo that you all decided on – it’s excellent! Moving on, your use-cases are beyond excellent – some of the most professional, and thorough ones I’ve seen; great job there!
In summary; great work this far – I can’t wait to see the final product!

## Slide 46: Zac Feedback
Week 5
Observations:
I feel like a broken record – but when the shoe fits: Awesome stuff this week, again! I continue to be amazed at not only the quality of work you all are producing – but in the highly collaborative manner in which you are doing it! Bravo!
Insights:
Your wireframes are absolutely magnificent! Not only are they clear and concise, and very user friendly – but you adhered to one of the BIGGEST best-practices in design today: “Mobile-First”. By knowing your Personas well, you know that a mobile experience is a must-have. (and you are probably keen to the fact that as of 2017 – Mobile has overtaken Desktop as the dominant browser). Therefore, when you designed your application to work and fit on a mobile device, you are guaranteeing all your users will have a great experience, regardless of the size of their screen. Incredible job! Can’t wait to see the final product in action!

## Slide 47: Action Items – Week 5
Feedback from Zac
  Estimation record
  State transition diagram
Week 5 Deliverables
  Mock-ups / Wireframes
  Complete Coding
  Report
Presentation
  Decision Required - 02/25 @ 14:00 EST
  Is report different from presentation? - No